## Master Schedule - SPMS
[8 empty] | Program Mgr |  |  |  |  | PC Manager |  |  | Purchasing Manager |  |  | Quality Manager |  |  |  | Program Mgr:
[8 empty] | Date:_______ |  |  |  |  | Date:_______ |  |  | Date:_______ |  |  | Date:_______ |  |  |  | Name:
SUPPLIED PARTS MASTER SCHEDULE (SPMS) | [22 empty] | Phone:
Master Schedule | [22 empty] | Email:
|  |  | CHANGE MANAGEMENT CONTROL | [6 empty] | 2013 |  |  |  | 2014 | [11 empty] | 2015
Program:
[Program Name Here] |  |  | Change Level | ECI # | Part Level | ECI Receipt Date | ECI Implementation Leadtime: (weeks) | Implementation Target Trial on ECI | Off Tool Part Available (Date) | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Supplier Name: | [9 empty] | N-17 | N-16 | N-15 | N-14 | N-13 | N-12 | N-11 | N-10 | N-9 | N-8 | N-7 | N-6 | N-5 | N-4 | N-3 | N-2 | N-1 | N | N+1
[Supplier Name Here] | bar: Dec to Mar
Supplier Code: | bar: Dec to Mar
[Supplier Code Here] | bar: Dec to Mar
Part No.: [Part Number Here] | bar: Dec to Mar
Part Name: [Part Name Here] | bar: Dec to Mar
Part Ranking: [Part Ranking Here] | bar: Dec to Mar
Production Preparation Location: | bar: Dec to Mar
North America | bar: Dec to Mar
Japan | bar: Dec to Mar
Other | bar: Dec to Mar
Drawing Detail: [Drawing Level Here] | bar: Dec to Mar
[Drawing Revision and Date Here] | bar: Dec to Mar
| # | ITEM | Supplier Comments |  |  | Target Start Date | Actual Start Date | Target Completion Date | Actual Completion Date | Sep: 2004; Jan: 2005; Jan: 2006
[10 empty] | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
QUALITY
SQAM Requirements | 1 | SUPPLIER TRAINING | QAPP RELEASE | - - - - | TMMK QE = Lead
| 2 | DESIGNATE SUPPLIER REPRESENTATIVE | GENZU or RDDP drawing release | + 4 weeks | update as necessary
| 5 | PART EVALUATION PLAN - DRAFT | GENZU or RDDP drawing release | + 4 weeks | reference part drawing for testing requirements
| 6 | C/F PROPOSAL WITH DRAWINGS | GENZU or RDDP drawing release | + 4 weeks | gage must be complete before part is off tool
| 7 | PFMEA | MAR, 2005 | + 4 weeks | update as necessary
| 7a | QCMS
| 8 | MQC / CONTROL PLAN | MAY, 2005 | + 4 weeks | update as necessary
| 9 | SAMPLE DATA SHEET PLAN | GENZU or RDDP drawing release | + 4 weeks | reference Part Insp Std
| 10 | IDENTIFICATION & TRACEABILITY | GENZU or RDDP drawing release | + 4 weeks | include on Part Insp Std
| 11 | INSPECTION STD - DRAFT | GENZU or RDDP drawing release | + 4 weeks | revise as required
| 12 | INSPECTION STD - FINAL | PROD DRAWING RELEASE | + 4 weeks | + 2 weeks for ASA drawing
| 13 | C/F COMPLETION / APPROVAL | OFF TOOL PART | - 3 weeks | completion - before O/T approval - during C/F
| 14 | SUPPLIER PROCESS AUDIT | JAN, 2005 | as needed
| 15 | REQUEST FOR PARTS / COMPONENTS | JAN, 2005 | as needed | all requests may not be fulfilled
| 16 | COLOR APPROVAL - INTERIOR | US C/F | before 1A
| 17 | COLOR APPROVAL - EXTERIOR | CSP | + 4 weeks
| 18 | GRAIN REVIEW / APPROVAL | GRAIN AUTHORIZATION | + 6 weeks | do not grain until authorized by TMMK QE
grained parts by 1A
| 19 | PART EVALUATION PLAN WITH RESULTS | 1st PART SUBMITTAL | each month | submit updates BY 5th of each month
|  |  |  | each trial | submit with parts & to QE Specialist
| 20 | SAMPLE DATA RESULTS | 1st PART SUBMITTAL | each trial | include Part Passing ratio on data sheet
| 20a | Problem Follow Sheet
| 21 | SHORT TERM PROCESS CAPABILITY STUDY | CONFIRMATION VEHICLE | each trial | Pc items from Part Insp Std
| 22 | LONG TERM PROCESS CAPABILITY STUDY | OFF PROCESS | 45 days after SOP (latest) | Pc items from Part Insp Std
| 23a | Request for Provisional Approval
| 23b | PROVISIONAL APPROVAL | C/F | before HVPT | include results from Part Eval Plan
| 24 | HIGH VOLUME PRODUCTION TRIAL | OFF PROCESS | after PA
| 25 | BOUNDARY SAMPLES - FINALIZE | C/F | before HVPT | update / crosscheck with Insp Std
| 26 | INITIAL MASS PRODUCTION QUALITY CONFIRMATION | LV QCS | during volume ramp up | reference on MQC
| 27 | FINAL APPROVAL | SOP + 30 | as required | FA may be granted at PA timing by TMMK QE
Quality Result KPI's | # | Quality Result Indicator | DESCRIPTION |  | Submission Document
| 1 | Part Completion | Part Drawing and Inspection Standard Requirements |  | Rollup of Result (# 2,3 ,4,5) below
| 2 | Part Accuracy Passing Ratio | Part Accuracy Requirements agreed to per Sample Parts Data Sheet. (Generally Dimensional,some perf) |  | Sample Parts Data Sheet
| 3 | Part Color Approval Ratio | Must achieve part color approval by TMMK QE per requirement |  | Color/Grain Document
| 4 | Part Grain Approval Ratio | Must achieve part grain approval per requirement |  | Color/Grain Document
| 5 | Part Performance Passing Ratio | Per Part Drawing and Inspection Standard (as agreed in PEP) |  | Part Evaluation Plan Results
PROCESS READINESS
1.1 Trial Build Plan
| 1.1.1 | ADVICS Due Date
| 1.1.2 | Parts Shipping Date
| 1.1.3 | Trial Build Event
| 1.1.4 | Raw Material / Component Part Receipt
1.2 Technical Information Management
| 1.2.1 | Production Drawing Receipt
| 1.2.2 | CAD Receipt (if applicable)
| 1.2.3 | Receipt of Approved Drawing
1.3 Facility Construction / Expansion
| 1.3.1 | Construction Plan
| 1.3.2 | Construction Schedule
1.4 Tooling Completion (includes all sub-component tooling)
| 1.4.1 | Tool Design / Kickoff
| 1.4.2 | Tool Build / Modification / Tuning
| 1.4.3 | Tooling Safety and Environmental Impact Review
| 1.4.4 | 1st Production Sample (Tool Supplier)
| 1.4.5 | Tool Shipment and Receipt at Mass Production Location
| 1.4.6 | Tool Installation / Tuning
| 1.4.7 | On-site Production Sample
1.5 Equipment / Fixtures Preparation
| 1.5.1 | Equipment Design / Kickoff
| 1.5.2 | Equipment Build / Modification / Tuning
| 1.5.3 | Jig / Fixture Schedule
| 1.5.4 | Equipment Safety and Environmental Impact Review
| 1.5.5 | Equipment Pre-acceptance (@ Builder location)
| 1.5.6 | Equipment Shipping and Receipt @ Mass Production Location
| 1.5.7 | Equipment Final Acceptance Trials
| 1.5.8 | Process Ready (Off-Process Achievement)
1.6 Process Documentation
| 1.6.1 | Set-Up / Change-Over Instructions
| 1.6.2 | Machine Parameter Control
| 1.6.3 | Standardized Work / Work Instructions
| 1.6.4 | Preventive Maintenance Schedule
1.7 Hiring and Training
| 1.7.1 | Hiring
| 1.7.2 | Training
1.8 Sub-Supplier Process Readiness
| 1.8.1 | Sourcing
| 1.8.2 | Trial Build Plan
| 1.8.3 | Quality Confirmation / Approval
| 1.8.4 | Capacity Confirmation
| 1.8.5 | Packaging
| 1.8.6 | Logistics Route Plan
1.9 Capacity and Through-Put Confirmation
| 1.9.1 | Capacity Planning
| 1.9.2 | Through-Put Planning
| 1.9.3 | Through-Put Confirmation
1.10 Production Readiness
| 1.10.1 | Quality Assurance Self Assessment
| 1.10.2 | HVPT Checklist
T2
T1
Proto
HVPT
19
14
PPAP Approval
Production Parts List Issued
SOP

## Tooling and Equip - TEP
[8 empty] | ADVICS | [6 empty] | REV | REASON | [6 empty] | DATE
[8 empty] | Quality Assurance Manager |  | Purchasing Manager |  | Coordinator
SUPPLIED PARTS MASTER SCHEDULE (SPMS)
Tooling and Equipment Preparation Sheet (TEP)
[5 empty] | 2013 |  |  |  | 2014 | [11 empty] | 2015
Program: |  |  |  | Project Targets: | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep |  | Nov | Dec | Jan | Feb | Mar
[Program Name Here] |  |  |  |  | N-17 | N-16 | N-15 | N-14 | N-13 | N-12 | N-11 | N-10 | N-9 | N-8 | N-7 | N-6 | N-5 | N-4 | N-3 | N-2 | N-1 | N | N+1
Supplier Name: |  |  |  | ● Off Tool at T1 ● Off Process at T1 ● No Critical Flow-out ● No Launch Disruptions
[Supplier Name Here]
Supplier Code:
[Supplier Code Here]
Part No.: [Part Number Here]
Part Name: [Part Name Here]
Part Ranking: [Part Ranking Here]
Production Preparation Location:
North America
|  | Japan | ADVICS MASTER SCHEDULE
Other
TO BE ISSUED BY ADVICS
Drawing Detail: [Drawing Level Here]
[Drawing Revision and Date Here]
| ITEM |  | Document Submission Timing | Expectation | 2013 Sep: 2013; 2014 Jan: 2014 |  |  |  | 2015
[5 empty] | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1.1 Trial Build Plan
| 1.1.1 | ADVICS Master Schedule Receipt (APMS) | SPMS (Beginning N-18) | Expectation: The supplier should develop a trial build plan including the 5 key items to the left. The timing should be detailed in the SPMS.
| 1.1.2 | ADVICS Due Date
| 1.1.3 | Parts Shipping Date
| 1.1.4 | Trial Build Event
| 1.1.5 | Raw Material / Component Part Receipt
1.2 Technical Information Management
| 1.2.1 | Prototype/Preparation Drawing Receipt (J,T,Z Level) | SPMS (Beginning N-18) (as necessary) | Expectation: The supplier should develop the part submission plan based on best available drawing. G Level drawings should be available and complied with prior to PPAP approval being granted.
| 1.2.2 | Production Drawing Receipt (G Level)
| 1.2.3 | Receipt of Approved Production Drawing
1.3 Facility Construction / Expansion / New Production Location
| 1.3.1 | Construction / Transfer Plan | Detail schedule (as requested) | Expectation: The supplier should develop a plan and manage the construction schedule to ensure readiness by agreed to timing. Timing range from site selection through handover.
| 1.3.2 | Construction / Transfer Schedule
| 1.3.3 | Facilities / Equipment Validation Plan
1.4 Tooling Preparation (includes all sub-component tooling)
| 1.4.1 | Tool Design / Kickoff | Detail schedule (as requested) | Expectation: Tool Kickoff should occur upon receipt of Prototype/Preparation Drawings. The supplier should actively manage all elements of the development and build schedule to ensure achievement of Off-Tool targets as communicated by the Project Master Schedule.
| 1.4.2 | Tool Build / Modification & Tuning
| 1.4.3 | Tooling Safety and Environmental Impact Review
| 1.4.4 | 1st Production Sample (Tool Supplier )
| 1.4.5 | Tool Shipment and Receipt at Mass Production Location
| 1.4.6 | Tool Installation / Tuning
| 1.4.7 | On-site Production Sample
1.5 Equipment / Fixtures Preparation
| 1.5.1 | Equipment Design / Kickoff | Detail schedule (as requested) | Expectation: The supplier should actively manage all elements of the development and build schedule to ensure achievement of Off-Tool and Off-Process targets as communicated by the Project Master Schedule.
| 1.5.2 | Equipment Build / Modification & Tuning
| 1.5.3 | Jig / Fixture Schedule
| 1.5.4 | Equipment Safety and Environmental Impact Review
| 1.5.5 | Equipment Pre-Acceptance Trial (@ Builder Location)
| 1.5.6 | Equipment Shipping and Receipt @ Mass Production Location
| 1.5.7 | Equipment Final Acceptance Trials
| 1.5.8 | Process Ready (Off-Process Achievement)
1.6 Process Documentation
| 1.6.1 | Set-Up / Change-Over Instructions | No documentation required. | Expectation: Drafts are developed during the Pre-acceptance stage, improved through final acceptance and ready to support team member training and Off-Process trials.
| 1.6.2 | Machine Parameter Control
| 1.6.3 | Standardized Work / Work Instructions
| 1.6.4 | Preventive Maintenance Schedule
1.7 Hiring and Training
| 1.7.1 | Hiring | No documentation required (detailed schedule available if requested) | Expectation: Hiring / Training Plan adequate to achieve Off-Process requirement (part produced by production operators), and all required team members trained to support Mass Production Volume at Ramp Up to SOP timing.
| 1.7.2 | Training
1.8 Sub-Supplier Process Readiness
| 1.8.1 | Sourcing | No documentation required. | Expectation: ADVICS suppliers are responsible to aggressively manage all aspects of their entire supply chain. Management should include the elements listed. Key Point: ADVICS supplier achievement of Off-Tool and Off-Process is contingent on sub-supplier achievement of Off-Tool and Off-Process. Key Point: The ADVICS supplier is responsible for interaction with direct supply component supplier and notification to ADVICS Purchasing if problems or conflicts arise.
| 1.8.2 | Trial Build Plan
| 1.8.3 | Quality Confirmation / Approval
| 1.8.4 | Capacity Confirmation
| 1.8.5 | Packaging
| 1.8.6 | Logistics Route Plan
1.9 Capacity and Through-Put Confirmation
| 1.9.1 | Capacity Planning | Supplier Capacity Survey | Expectation: The suppliers should clearly understand their available capacity (plant / equipment / process) and develop targets for cycle time, uptime, scrap and production rate to meet the ADVICS daily volume requirement. Develop and execute a trial build plan to ensure achievement of targets (cycle time, uptime, scrap and production rate.)
| 1.9.2 | Through-Put Planning | HVPT Checklist
| 1.9.3 | Through-Put Confirmation | HVPT Tracking Sheet
1.10 Production Readiness
| 1.10.1 | HVPT Checklist | HVPT Checklist | Expectation: Suppliers should utilize as self-auditing tool at each trial with results provided to ADVICS Purchasing.
SOP
T2
T1
Proto
HVPT
19
14
PPAP Approval
Production Parts List Issued
6
31
26
Prototypes
Due
T1 Due
T2 Due

## Quality Assurance Plan - QAP
[8 empty] | ADVICS | [6 empty] | REV | REASON | [6 empty] | DATE
[8 empty] | Quality Assurance Manager |  | Purchasing Manager |  | Coordinator
SUPPLIED PARTS MASTER SCHEDULE (SPMS)
Quality Assurance Planning Sheet (QAP)
[5 empty] | 2005 |  |  |  | 2006 | [11 empty] | 2006
Program: |  |  |  | Project Targets: | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep |  | Nov | Dec | Jan | Feb | Mar
[Program Name Here] |  |  |  |  | N-17 | N-16 | N-15 | N-14 | N-13 | N-12 | N-11 | N-10 | N-9 | N-8 | N-7 | N-6 | N-5 | N-4 | N-3 | N-2 | N-1 | N | N+1
Supplier Name: |  |  |  | ● Off Tool at T1 ● Off Process at T1 ● No Critical Flow-out ● No Launch Disruptions
[Supplier Name Here]
Supplier Code:
[Supplier Code Here]
Part No.: [Part Number Here]
Part Name: [Part Name Here]
Part Ranking: [Part Ranking Here]
Production Preparation Location:
North America
|  | Japan | ADVICS MASTER SCHEDULE
Other
TO BE ISSUED BY ADVICS
Drawing Detail: [Drawing Level Here]
[Drawing Revision and Date Here]
| ITEM |  | Document Submission Timing | Expectation | 2005 Sep: 2005; 2006 Jan: 2006 |  |  |  | 2007
[5 empty] | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1.1 Trial Build Plan
| 1.1.1 | ADVICS Master Schedule Receipt (APMS) | SPMS (Beginning N-18) | Expectation: The supplier should develop a trial build plan including the 5 key items to the left. The timing should be detailed in the SPMS.
| 1.1.2 | ADVICS Due Date
| 1.1.3 | Parts Shipping Date
| 1.1.4 | Trial Build Event
| 1.1.5 | Raw Material / Component Part Receipt
1.2 Technical Information Management
| 1.2.1 | Prototype/Preparation Drawing Receipt (J,T,Z Level) | SPMS (Beginning N-18) (as necessary) | Expectation: The supplier should develop the part submission plan based on best available drawing. G Level drawings should be available and complied with prior to PPAP approval being granted.
| 1.2.2 | Production Drawing Receipt (G Level)
| 1.2.3 | Receipt of Approved Production Drawing
1.3 Process Quality Planning Documents
| 1.3.1 | Process FMEA (PFMEA) | Per the PRC | Expectation: The supplier should develop the core quality documents prior to sample preparation and no later than prior to PPAP submission. Cross-functional teams should be used to develop these documents. The PPAP Request Cover Sheet, PSW, and Dimensional Study Report shall always be provided. Additional PPAP Reports are to be submitted as requested by the Purchasing or Quality Departments.
| 1.3.2 | Special Characteristics List (SCL)
| 1.3.3 | Guage / Check Fixture / POKA YOKE List
| 1.3.4 | Prototype / Pre-launch Control Plan
| 1.3.5 | Production Control Plan
| 1.3.6 | Process Control Checksheets / SPC Charts
| 1.3.7 | Receiving Inspection Plans
| 1.3.8 | PPAP Submission
1.4 Product Compliance Confirmation
| 1.4.1 | Special Characteristics Capability Map | Per the PRC | Expectation: The PPAP Request Cover Sheet, PSW, and Dimensional Study Report shall always be provided. Additional PPAP Reports are to be submitted as requested by the Purchasing or Quality Departments.
| 1.4.2 | Functional Performance Report
| 1.4.3 | Dimensional Performance Report
| 1.4.4 | Color / Grain Appearance Report
| 1.4.5 | Material Report
| 1.4.6 | MSA Studies
1.10 Production Readiness
| 1.10.1 | HVPT Checklist | Per the PRC | Expectation: Suppliers should utilize as self-auditing tool at each trial with results provided to ADVICS Purchasing.
SOP
2A
1A
Proto
HVPT
19
14
PPAP Approval
Production Parts List Issued
6
31
26
Prototypes
Due
1A Due
2A Due

## KPITv6 (hidden)
KPI - Tracking (KPIT)
[5 empty] | 2005 | [35 empty] | 2006
Supplier __________________________ Supplier Code_____________________ Part Number(s)____________________ Part Name(s)______________________
[5 empty] | Jan |  |  | Feb |  |  | Mar |  |  | Apr |  |  | May |  |  | Jun |  |  | Jul |  |  | Aug |  |  | Sep |  |  | Oct |  |  | Nov |  |  | Dec |  |  | Jan |  |  | Feb |  |  | Mar
# | ITEM | Key Points |  | 100% Completion Target Date | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge | Target | Actual | Judge
Quality Readiness
SPMP ref # | Quality Documentation (SQAM Requirements)
12 | Inspection Standard (Final) |  |  | Jan. End 05 | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
5 | Part Evaluation Plan |  |  | Jan. End 05 | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
7 | PFMEA |  |  | April 05 | [9 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
8 | MQC |  |  | June 05 | [15 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
13 | Part Checking Fixture Approval |  |  | July 05 | [18 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
20 | Sample Data Sheet | Must submit with each trial (with parts, and IS copy) |  | Each Trial | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
21 | Capability Studies | Must submit with Sample Data Sheets for Pc Items |  | Each Trial | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
19 | Evaluation Plan Result | Submit Doc Jan end and 5th of each month |  | Monthly | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
25 | Boundary Samples | Boundary Sample Submission From (Sept 05~Nov 04) |  | Nov 05 | [30 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
10 | ID and Traceability |  |  | Jan End 05 | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
Part Approvals (SQAM Requirements)
23 | Provisional Approval | Functional Parts 2A end All other parts Prior 2A |  | Dec.Mid 05 | [33 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100%
27 | Final Approval | Automatic with PA unless determined otherwise |  | March 06 | [42 empty] | 100%
Quality Result KPI's
1 | Part Completion Ratio | 100% 2A |  | Oct. end 05 | [27 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
2 | Part Accuracy Passing Ratio | 100% 1A end , 97% @ 044L CV |  | Sep end 05 | [12 empty] | 97% |  |  | 97% |  |  | 97% |  |  | 97% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
3 | Parts Color Approval Ratio | 100% 1A |  | Oct. 05 | [27 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
4 | Part Grain Approval Ratio | 100% 1A end |  | Oct. 05 | [27 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
5 | Part Performance Passing Ratio | 100% 2A |  | Oct. end 05 | [27 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
Process Readiness
Trial Build Plan
1 | Trial materials ordered/delivery scheduled | See judge criteria above
2 | Trial materials received on schedule, quality confirmed | See judge criteria above
Facility Construction / Expansion
1 | Construction plan |  |  | 1A
Tooling/Fixture & Equip Completion
1 | Tooling/fixtures kicked off (O, D or X) |  |  | OP Target | [24 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
2 | First tool/fixture on schedule (O, D or X) | [18 empty] | 100% | [8 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
3 | First tool/fixture completion ratio | [6 empty] | 50% |  |  | 100% | [17 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
4 | Remaining tools/fixtures on schedule (O, D or X)
5 | Remaining tools/fixtures completion ratio | [9 empty] | 25%
6 | Equipment/fixtures kicked off (O, D or X)
7 | All equipment/fixtures on schedule (O, D or X)
8 | All equipment/fixtures completion ratio | [6 empty] | 25% |  |  | 75%
Process Documentation
1 | PRC Process Documentation Ranking |  |  | OP Target | [27 empty] | x | x |  | x | x |  | x | x |  | x | x |  | x | x |  | x | x
Hiring + Training
1 | PRC Hiring + Training Ranking |  |  | OP Target | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  | x | x |  | x | x |  | x | x |  | x | x |  | x | x |  | x | x |  | x | x |  | x | x |  | x | x |  | x | x
Sub Supplier Process Readiness
1 | Preparation Management | # parts progress to schedule/outsourced components |  | OP Target |  |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
Capacity and Through-Put Confirmation
1 | Through-Put Planning | N-18, N-12, N-6 Requirement vs Capacity (O, D, X)
2 | Through-Put Confirmation | >60% @ 1A, > 85% @ 2A, 100% @ SQCS |  |  | 60% | [8 empty] | 85% | [11 empty] | 85% | [14 empty] | 100%
Operations Readiness
*Master schedule for all PC items completed & submitted to TMMK. | [13 empty] | 100%
1) Packaging Process
| A) Preliminary proposal submitted | Submission of document - PC judgement | [5 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| B) Final Packaging ordered complete | Submission of document - PC judgement | [20 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| C) Production Packaging received 100% | Submission of document - PC judgement | [32 empty] | 100% | 2A |  | 100% |  |  | 100% |  |  | 100%
| D) Temporary Packaging Planning | Submission of document - PC judgement | [32 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100%
2) Internal Parts Material Conveyance
| A) Submit completed internal material & conveyance flow method | Submission of document - PC judgement | [17 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| B) STD work for new parts process completed/submitted | Submission of document - PC judgement | [32 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| C) Training on new standard work completed | [33 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| D) Equipment requirements plan completed | [24 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| E) Additional equipment requirement ordered | [27 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| F) Ordered equipment received complete | [33 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100%
3) Parts Ordering Readiness
| A) Overseas ordering plan submitted | Submission of document - PC judgement | [23 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| B) Parts ordered - Overseas | [24 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| C) North American parts -- plan submitted | Submission of document - PC judgement | [23 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| D) Parts ordered - North American | [30 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| E) Parts requiring external processing identified. Part list submitted to TMMK. | Submission of document - PC judgement | [23 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
4) Finished Goods Order & Inventory Mgmt.
| A) Submit developed production plan to support shipping requirements | Submission of document - PC judgement | [26 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| B) Confirm shipping systems standard processes complete | ASN & OWK system checked/confirmed. EDI receipt checked/confirmed. 13 week pre-notice. Access to Toyota supplier.com. SKIPI system access. | [32 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| C) Inventory Management Process (Picking / Staging, etc.) | Submission of document - PC judgement | 2A = 100% | [28 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| D) Standard work for short shipment/mixed kanban process documented & submitted | Submission of document - PC judgement | [29 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| E) Supplier Production Acceleration Schedule submitted on TMMK Provided Plan vs. Actual Document 100% Daily S-A-B | Submission of document - PC judgement * Daily submission through SOP | [32 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100%
NO | CONCERN ITEMS | [5 empty] | COUNTERMEASURES | [26 empty] | RESPONSIBILITY | [6 empty] | TIMING
SQAM
Sec App
SQAM
Sec App
Export Parts C/F
(at Supplier)
SB
1W
SO
MPTW
LV
QCS
HV
QCS
SOP
MPTA
1A
C/F
Judge criteria
X No Good Condition, Will miss target
D Recovery plan in place, no impact
O Meet target
CV (U.S.)
DEPENDING ON YOUR SPECIFIC PART SITUATION, SOME TARGETS MAY REQUIRE ADJUSTMENT.
NEGOTIATE WITH TOYOTA CONTACT.

## PRCv3 (hidden)
PRODUCTION READINESS CHECKSHEET
PROJECT CODE:
SUPPLIER: |  |  |  |  | SUPPLIER LOCATION: |  |  |  | CODE:
PART NAME:
PART NUMBER(S):
COMPLETED BY: |  |  |  |  | DEPT: | EXT: | Expectation/
[7 empty] | Supplier Judgement | [6 empty] | Toyota Judgement
ITEM | [6 empty] | CF | CV | 1A | MPT | LV | HV | SQCS | CF | CV | 1A | MPT | LV | HV | SQCS | Follow Up/Comments |  |  |  | WHO | WHEN
I. PCE: Tooling & Equipment /Fixutes
1. Tooling Readiness |  |  |  |  | Tool complete to ECI target trials |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o
Overall Rating |  |  |  |  | Tool in mass production location |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | Graining complete |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
[5 empty] | Additional cavities complete |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
[5 empty] | Tool meets Quality requirements |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
2. Equipment & Fixtures |  |  |  |  | Complete to ECI target trials |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | In mass production location (primary |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | & secondary)
[5 empty] | Preventive maintenance documented |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
II. PCE: ECI Implementation
1. ECI |  |  |  |  | ECI log updated |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o | [5 empty] | y
Overall Rating
CF | CV | 1A | 2A | QCS
III. PCE: Process Documentation
1. Problem Follow Sheet (PFS) |  |  |  |  | System in place to capture and manage |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o
Overall Rating |  |  |  |  | problems (with responsibility & timing)
CF | CV | 1A | 2A | QCS | Problems from previoius trials closed |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o
2. Setup/Change Over Instructions |  |  |  |  | Procedure documented |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | Located lineside |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | Conduct trials to confirm procedure |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
(results documented)
3. Line balance |  |  |  |  | Process/line balance plan drafted |  |  | o | [6 empty] | o
Overall Rating |  |  |  |  | Line balance in place with no negative |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | impact to quality or capacity
4. Work In Progress |  |  |  |  | WIP locations between processes |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | identified within cell (if needed)
CF | CV | 1A | 2A | QCS | Min/Max targets identified by supplier |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
[5 empty] | WIP standards maintained |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
5. Downtime Tracking |  |  |  |  | Downtime tracking system in place |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | Method to manage downtime |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | countermeasures
6. Work Instructions |  |  |  |  | Work instruction completed |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | Located at process |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | Clear and effective (what, how |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
frequency, defect disposition)
[5 empty] | Work instruction approved (signed |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
& dated)
[5 empty] | Operators follow work instruction |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
7. Process Parameters |  |  |  |  | Documented on MQC (baseline & range) |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | Document available lineside |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | Method in place to confirm |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Documented (tracking, PFS)
Frequency set
Evidence of use
Problem reaction determined
[5 empty] | Parameters in spec procedure |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
8. Preventive Maintenance |  |  |  |  | Maintenance procedure documented |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | Frequency determined |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | Tracking procedure |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
[5 empty] | Responsibility is clear (operator vs. |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
maintenance)
[5 empty] | Spare parts identifed |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
[5 empty] | Spare parts management system |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
IV. PCE: Hiring + Training
1. Hiring |  |  |  |  | Plan established (differentiate |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | permenate/contractor/temporary)
CF | CV | 1A | 2A | QCS | 1 shift hired |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
[5 empty] | All shifts hired |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
2. Training |  |  |  |  | Taining plan established |  |  | o | o | o | o | o | o |  | o | o | o | o | o | o
Overall Rating |  |  |  |  | Versatility chart/schedule documented |  |  | o | o | o | o | o | o |  | o | o | o | o | o | o
CF | CV | 1A | 2A | QCS | and up dated
[5 empty] | One shift trained, producing to target |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
[5 empty] | All shifts trained, producing to target | [7 empty] | o | [6 empty] | o
3. Operators |  |  |  |  | Mass production operators used to |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | make trial parts.
CF | CV | 1A | 2A | QCS
V. PCE: Sub-Supplier Preparation & Readiness
1. Sub-supplier raw materials |  |  |  |  | Raw material specifications meets |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o
Overall Rating |  |  |  |  | latest drawing requirements
CF | CV | 1A | 2A | QCS | Chosen source passed all validation |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o
testing
[5 empty] | Long term purchase order in place |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
2. Sub-supplier tooling |  |  |  |  | Tools complete to ECI target trial |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o
Overall Rating |  |  |  |  | In mass production location |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | Additional cavities finished |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
[5 empty] | Graining complete |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
[5 empty] | Material/component sheet updated |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
3. Sub-supplier equipment/fixtures |  |  |  |  | Equipment/fixtures complete to target |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o
Overall Rating |  |  |  |  | ECI trials
CF | CV | 1A | 2A | QCS | In mass production location |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
[5 empty] | Capacity studies completed |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
and passed
[5 empty] | Preventive maintenance requirements |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
documented
4. Sub-Supplier capacity |  |  |  |  | Systematic method to confirm |  |  | o | o | o | o | o | o |  | o | o | o | o | o | o | [5 empty] | y
Overall Rating |  |  |  |  | * Confirmation plan
CF | CV | 1A | 2A | QCS | * Tracking document
* Actual confirmation for
critical suppliers
[5 empty] | Capacity plan reviewed and approved |  |  | o | o | o | o | o | o |  | o | o | o | o | o | o
[5 empty] | Capacity confirmed acceptable |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
5. Quality Confirmation Activity
Overall Rating
CF | CV | 1A | 2A | QCS
6. Packaging Preparation
Overall Rating
CF | CV | 1A | 2A | QCS
7. Logistics Preparation
Overall Rating
CF | CV | 1A | 2A | QCS
VI. Capacity
1. Available time |  |  |  |  | Shared Line:
Overall Rating |  |  |  |  | Line load sheet indicated time |  | o | o | o | o | o | o | o |  | o | o | o | o | o | o
CF | CV | 1A | 2A | QCS | available for Toyota
Dedicated Line:
[5 empty] | Number of shifts required determined |  | o | o | o | o | o | o | o |  | o | o | o | o | o | o
(based on planned cycle time)
[5 empty] | Number of shifts confirmed (based on |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
actual cycle time)
2. Cycle time |  |  |  |  | Target cycle time determined |  | o | o | o | o | o | o | o |  | o | o | o | o | o | o
Overall Rating |  |  |  |  | Machine cycle times at 100% of target |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | Operators > 60% target |  |  |  | o | [6 empty] | o
[5 empty] | Operators > 85% target |  |  |  |  | o | [6 empty] | o
[5 empty] | Operators = 100% target | [5 empty] | o | o | [5 empty] | o | o
[5 empty] | Document on HVPT trial status sheets |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
3. Uptime |  |  |  |  | Determine uptime target |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o
Overall Rating |  |  |  |  | Confirmed @ 60% |  |  |  |  | o | [6 empty] | o
CF | CV | 1A | 2A | QCS | Confirmed @ 85% | [5 empty] | o | o | [5 empty] | o | o
[5 empty] | Confirmed @ 100% | [7 empty] | o | [6 empty] | o
4. Defect Ratio |  |  |  |  | Defect Target rate system to capture, |  | o | o | o | o | o | o | o | o | o | o | o | o | o | o
Overall Rating |  |  |  |  | analyze, countermeasure definition
CF | CV | 1A | 2A | QCS | No negative impact to capacity | [5 empty] | o | o | o |  |  |  |  | o | o | o
5. Change-over |  |  |  |  | Procedure documented |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
Overall Rating |  |  |  |  | Located lineside |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
CF | CV | 1A | 2A | QCS | Target cycle time established |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
[5 empty] | Target cycle time confirmed |  |  |  |  | o | o | o | o |  |  |  | o | o | o | o
[5 empty] | Team members trained |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
[5 empty] | Conduct trials to confirm procedure |  |  |  | o | o | o | o | o |  |  | o | o | o | o | o
(results documented)
6. Trial Results | [8 empty] | o | o | o | o | o |  |  | o | o | o | o | o | Event Name | Target | Actual | Result
Overall Rating | [20 empty] | Cycle Time
CF | CV | 1A | 2A | QCS | [16 empty] | Uptime %
Defect %
Good pcs/hr
Purpose: Open boxes represent timing when line item should be confirmed or completed.
If line item is complete: Supplier / Toyota should fill in the box and rate the item
O : All criteria complete to plan
D : 1 criteria not complete to plan
(countermeasure in place AND
will make next event)
X : 1 criteria not complete to plan
(no countermeasure in place)
-or-
1 criteria not complete and will
will miss next event
Overall Ratings
O = No X's and no D's
D = No X's and 1 or more D's
X = X in any Rating
Production Readiness Rating
Tooling and Equipment Rating
Process Documentation + Hiring & Training
Sub-Supplier Rating
Capacity & Through-Put Rating
Supplier Evaluation
Production Readiness Rating
Tooling and Equipment Rating
Process Documentation + Hiring & Training
Sub-Supplier Rating
Capacity & Through-Put Rating
Toyota Evaluation
Request Greg Wilkins to lead development of these criteria and associated timing (including consensus with TMMC / NUMMI).
Target completion: 4/8/05

## 044L QAPP (hidden)
[24 empty] | REV | REASON | [6 empty] | DATE
|  | 331W QUALITY ASSURANCE PROJECT PLAN | [21 empty] | --- | INITIAL RELEASE | [6 empty] | 05/24/04
[24 empty] | 1 | Mass Production code = 331W / updated Supplier Training detail | [6 empty] | 08/11/04
[24 empty] | 2 | Updated Supplier Training timing | [6 empty] | 10/28/04
|  |  | SQAM SECTION | APPENDIX |  |  |  | 2004 | [9 empty] | 2005 | [11 empty] | 2006
|  | SUPPLIER |  |  | Key Points: |  |  | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
|  | QUALITY |  |  | â Supplier access to drawings: |  |  | N-23 | N-22 | N-21 | N-20 | N-19 | N-18 | N-17 | N-16 | N-15 | N-14 | N-13 | N-12 | N-11 | N-10 | N-9 | N-8 | N-7 | N-6 | N-5 | N-4 | N-3 | N-2 | N-1 | N | N+1
|  | ASSURANCE |  |  | Design release + 7 calendar days
|  | MANUAL | [5 empty] | 2004 Jul: 17
â Requirements are based on submittal timing
ACTIVITY SCHEDULE
|  | (based on December, 2002 - Issue 3) |  |  | â Exceptions to timing on this document must
be negotiated with TMMK QE
â Parts completion target: 100% at 1A
OFFICIAL MASTER SCHEDULE
TO BE ISSUED BY PC
| # | ITEM |  |  | MILESTONE | SUBMITTAL | NOTE | 2004 Mar: 2004; 2005 Jan: 2005; 2006 Jan: 2006
[5 empty] | start from . . . |  |  | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
QAPP | 1 | SUPPLIER TRAINING |  |  | QAPP RELEASE | - - - - | TMMK QE = Lead | bar: 2004 Jun; 2004 Nov; 2005 Jan
| 2 | DESIGNATE SUPPLIER REPRESENTATIVE | 2 | A,B,C | GENZU | + 4 weeks | update as necessary | bar: 2004 Jul to 2004 Aug; 2005 Oct
| 3 | QAS | 12 | D,F | GENZU | + 4 weeks | submit updates BY 5th of each month | bar: 2004 Jul to 2004 Aug; 2005 Oct
| 4 | TPR | 12 | E,F | GENZU | + 4 weeks | submit updates BY 5th of each month | bar: 2004 Jul to 2004 Aug; 2005 Oct
| 5 | PART EVALUATION PLAN - DRAFT | 14 | G | GENZU | + 4 weeks | reference part drawing for testing requirements | bar: 2004 Jul to 2004 Aug; 2004 Oct; 2005 Jan
| 6 | C/F PROPOSAL WITH DRAWINGS | 16 | L | GENZU | + 4 weeks | gage must be complete before part is off tool | bar: 2004 Jul to 2004 Aug; 2004 Oct
| 7 | PFMEA | 17 | P | GENZU | + 4 weeks | update as necessary | bar: 2004 Jul to 2004 Aug; 2004 Oct; 2005 Apr; 2005 Dec
| 8 | MQC / CONTROL PLAN | 18 | Q | GENZU | + 4 weeks | update as necessary | bar: 2004 Jul to 2004 Aug; 2004 Oct; 2005 Apr; 2005 Dec
| 9 | SAMPLE DATA SHEET PLAN | 19 | H | GENZU | + 4 weeks | reference Part Insp Std | bar: 2004 Jul to 2004 Aug; 2004 Oct
| 10 | IDENTIFICATION & TRACEABILITY | 20 | J or K | GENZU | + 4 weeks | include on Part Insp Std | bar: 2004 Jul to 2004 Aug; 2004 Oct; 2005 Jan
| 11 | INSPECTION STD - DRAFT | 15 | I,J | GENZU | + 4 weeks | revise as required | bar: 2004 Jul to 2004 Aug; 2004 Oct
| 12 | INSPECTION STD - FINAL | 15 | I,J,K | PROD DWG RELEASE | + 4 weeks | revise as required | bar: 2004 Oct; 2005 Jan
| 13 | C/F COMPLETION / APPROVAL | 17 | L,M,N,AO | OFF TOOL PART | - 3 weeks | completion - before O/T approval - during C/F | bar: 2005 Jan; 2005 May; 2005 Jul
| 14 | SUPPLIER PROCESS AUDIT | 40 |  | JAN, 2005 | as needed | bar: 2005 Jan; 2005 Jun to 2005 Jul; 2005 Dec
| 15 | REQUEST FOR PARTS / COMPONENTS | 32 | Y | JAN, 2005 | as needed | all requests may not be fulfilled | bar: 2005 Jan to 2005 Feb; 2005 Jul; 2005 Sep
| 16 | COLOR APPROVAL - INTERIOR | 21 | S,T | C/F | before 1A | bar: 2004 Nov to 2005 Jan; 2005 Jun; 2005 Sep; 2005 Nov
| 17 | COLOR APPROVAL - EXTERIOR | 21 | S,T | CSP | + 4 weeks | bar: 2005 Jan; 2005 May; 2005 Sep; 2005 Nov
| 18 | GRAIN REVIEW / APPROVAL | 21 | T | GRAIN AUTHORIZATION | + 6 weeks | do not grain until authorized by TMMK QE | bar: 2005 Jan; 2005 Jul to 2005 Sep; 2005 Nov
grained parts by 1A
| 19 | PART EVALUATION PLAN WITH RESULTS | 14 | G,H,R | 1st PART SUBMITTAL | each month | submit updates BY 5th of each month | bar: 2005 Feb; 2006 Jan
[6 empty] | each trial | submit with parts | bar: 2005 Feb; 2005 May; 2005 Sep; 2005 Nov; 2006 Jan
| 20 | SAMPLE DATA RESULTS | 19 | H,R | 1st PART SUBMITTAL | each trial | include Part Passing ratio on data sheet | bar: 2005 Feb; 2005 May; 2005 Sep; 2005 Nov; 2006 Jan
| 21 | SHORT TERM PROCESS CAPABILITY STUDY | 13 |  | CONFIRMATION VEHICLE | each trial | Pc items from Part Insp Std | bar: 2005 Feb; 2005 May; 2005 Sep; 2005 Nov; 2006 Jan
| 22 | LONG TERM PROCESS CAPABILITY STUDY | 13 |  | OFF PROCESS | 45 days after SOP (latest) | Pc items from Part Insp Std | bar: 2005 Jun; 2006 Mar
| 23 | PROVISIONAL APPROVAL | 23 | X | C/F | before HVPT | include results from Part Eval Plan | bar: 2005 Jul; 2005 Nov
| 24 | HIGH VOLUME PRODUCTION TRIAL | 22 | V,W | OFF PROCESS | after PA | bar: 2005 Aug; 2005 Dec
QAPP | 25 | BOUNDARY SAMPLES - FINALIZE | 33 | Z | C/F | before HVPT | update / crosscheck with Insp Std | bar: 2005 Sep; 2005 Nov
| 26 | INITIAL MASS PRODUCTION QUALITY CONFIRMATION | 24 |  | LV QCS | during volume ramp up | reference on MQC | bar: 2006 Jan to 2006 Feb
| 27 | FINAL APPROVAL | 23 | X | SOP + 30 | as required | FA may be granted at PA timing by TMMK QE | bar: 2006 Mar
PRP | Tooling Completion
| 1 | Tool Design / Kickoff
| 2 | Tool Completion
| 3 | Tool Tuning
| 4 | Tool at Final Location
Equipment / Fixtures
| 1 | Equipment Design / Kickoff
| 2 | Equipment / Fixture Completion
| 3 | Equipment VTO (Vendor Tryout)
| 4 | Equipment TSO (Total System Tryout)
ECI Implementation
| 1 | Tooling / Equipment Modification
Process Documentation
| 1 | Set-Up / Change-Over Instructions
| 2 | Machine Paramenter Control
| 3 | Work Instructions
| 4 | Inspection Standards
Process Hiring and Training
| 1 | Hiring
| 2 | Training
Tier 2 Process Readiness
| 1 | Sourcing
| 2 | Preparation Confirmation
| 3 | Quality Approval
| 4 | Capacity Confirmation
| 5 | Packaging
| 6 | Logistics
PRP | Capacity and Through-Put Process
| 1 | Takt Time
| 2 | Machine Cycle Time (bottleneck)
| 3 | Cycle Time (total)
| 4 | Change-Over Time
| 5 | Downtime
| 6 | Capacity at N-18
| 7 | Capacity at N-12
| 8 | Capacity at N-6
| 9 | Operating Time
OMR | *Master schedule for all PC items completed & submitted to TMMK.
1) Packaging Process
A) Preliminary proposal approved/submitted
B) Final approval received
C) Packaging ordered
D) Packaging received
E) Temporary packaging approved/submitted
F) Temporary packaging ordered & received
2) Manpower Planning Process (hiring/training)
A) Submit additional manpower required plan
B) Hiring/rotation plan developed/submitted
C) Submitted new T/M's hired/rotation schedule
D) Submitted completed schedule T/M's trained on process(es)
3) Internal Parts Conveyance
A) Submitted completed internal material & conveyance flow method developed
B) STD work for new parts process completed/submitted
C) Training on new standard work completed
D) Equipment requirements plan completed
E) Additional equipment requirement ordered
F) Ordered equipment received complete
OMR | 4) Parts Ordering
A) O/S (anything outside US/Canada) parts identified & plan developed to order correct quantity need to support: Internal process/equipment confirmation, T/M training, QCS trial, internal linefill, TMMK linefill, SOP orders (including shipping system fill), ramp-up plan, & internal safety. Plan submitted.
B) Parts ordered
C) North American parts -- same as O/S. Plan submitted.
D) Parts ordered
E) Parts requiring external processing identified. List submitted to TMMK.
5) Inventory Management
A) Submitted developed production plan to support shipping requirements
B) Confirm shipping systems standard processes complete
*EDI receipt checked/confirmed. 13 week pre-notice
*OWK (One Way Kanban) system checked/confirmed
*ASN system checked/confirmed
*Parts picking & staging standard for daily shipments & submitted
*Standard work for short shipment process documented & submitted
*Access to Toyota supplier.com
*Understand SKIPI system
*Production Acceleration Schedule (to match ramp-up) & submitted
H
V
Q
C
S
331W SOP
330W SOP
EXPORT PARTS - LINE FILL 11/END
2A
2W
L
V
Q
C
S
1A
1W
SO
SB
J1A
J1W
A TRY
W TRY
SO
SB
JCF
Ý
PART DELIVERY TARGET
US TOOLING 26 WEEKS
JPN TOOLING 15 WEEKS
Ý
PART DELIVERY TARGET
Prod DWG Release
ASSY
@ JPN
C/V EVAL (JAPAN)
ASSY
@ JPN
C/V EVAL (US)
US EXPORT PARTS TOOLING 23 WEEKS
MODIFY
GENZU
SE
Ý
PROD VEH SPEC (before SE)
Ý
PROV PARTS LIST
Ý
PROD PARTS LIST FIX - ECI FREEZE
(BEFORE TOOLING K/O MTG)
Ý
PROD VEH SPEC FIX (before MODIFY)
QCS
NA export parts - TMMK 2A Timing - Must be Mass Production Quality
K4 DWG Review
SE DWG Review
Genzu DWG Review
HVPT
REQUEST
SHIP PARTS
SHIP BODIES
COLOR MASTER REQUEST
COLOR K/O
COLOR MATCH
FINAL
2A
COMPLETION
FINAL
FINAL
CONCEPT
Ý
STYLE APPROVAL
FINAL
DRAFT
DRAFT
FINAL
DRAFT
DRAFT
FINAL
FINAL
C/V - EXPORT PARTS
1A
2A
QCS
QCS
C/F
FINAL
CSP
GRAIN K/O
APPROVAL
Export Parts C/F (at Supplier)
I/S, C/F, PEP, QAPP
SAMPLE DATA, PFS,
BOUNDARY SAMPLES
COLOR & GRAIN
FINAL
FINAL
C/V - EXPORT PARTS
1A
2A
QCS
C/F
COLOR K/O
1A
C/V - EXPORT PARTS
1A
2A
QCS
C/F
DRAFT
DRAFT
C/F
Ý
PROD PARTS LIST
C/F ¿xË
C/F ¿xË
GAS
1A
DRAFT
DRAFT
DRAFT
DRAFT
DRAFT
EXPORT PARTS
NA DELIVERY PARTS